## FGH_Jembi WP
| # | [5 empty] | September |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January
Category |  | Task | Deliverable | Resp | Support | Status | 17-21 | 24-28 | 2018-01-05 | 2018-08-12 | 15-19 | 22-26 | 29-2/11 | 2018-05-09 | 2018-12-16 | 19-23 | 26-30 | 2018-03-07 | 2018-10-14 | 17-21 | 24-28 | 31/12-04/01 | 2018-07-11 | 14-18 | 21-25 | 28-01
Pre-Requisites | 1.1 | Setup Metadata Servers ( OpenMRS 1.11.x) | Metadata server running and accessible | Jembi | FGH | completed |  | x
| 1.2 | Setup Testing Environment (OpenMRS 1.11.x) | Testing Environment running and accessible | Jembi | FGH | ongoing |  | x
MasterCard Forms | 2.1 | Requirements gathering & definition for MasterCard Forms (incl. concept data mapping) | Requirements Document for MasterCard Forms | FGH | Jembi/MOH | completed | x | x | x | x |  |  | x
| 2.2 | Create new concepts for MasterCards | New concepts for MasterCards created | FGH | Jembi | ongoing |  |  |  |  | x
| 2.3 | Update HIV Drug Regimens concepts (TLD) | HIV Drug Regimens concepts updated on concept dictionary | FGH | Jembi | pending | [7 empty] | x
| 2.4 | MasterCards layout design & forms development OpenMRS 1.11.x | Forms developed for OpenMRS 1.11.x | FGH | Jembi | not started | [5 empty] | x | x | x | x
| 2.5 | User Acceptance and Testing for MasterCards OpenMRS 1.11.x | Test Results Report for MasterCards | Jembi | FGH/MOH | not started | [8 empty] | x
PEPFAR Reports | 3.1 | Requirements Gathering and definition for MER Indicators Report (including testing scenarios) | Requirements Document for MER Indicators | FGH | Jembi/CDC | ongoing |  | x | x | x | x | x | x | x | x | x
| 3.2 | Update MER Report Indicators according to Q1 equirements for 1.11.x | MER Reports developed for 1.11.x | FGH | Jembi | not started | [5 empty] | x | x | x | x | x
| 3.3 | Develop Reporting module for Q1 MER Indicators Reports | MER Reporting module developed for Q1 | Jembi | FGH | ongoing | [5 empty] | x | x | x | x | x
| 3.4 | User Acceptance and Testing for MER indicators | Test Results Report for MER Report | Jembi | FGH/CDC | not started | [8 empty] | x | x | x
MoH Reports | 4.1 | Requirements Gathering and Definition for MOH Reports | Requirements Document for MOH Reports | FGH | Jembi/MOH | ongoing |  |  |  | x | x | x | x
| 4.2 | Develop MoH Reports for OpenMRS 1.11.x | MOH Reports developed for 1.11.x | FGH | Jembi | not started | [10 empty] | x | x | x
| 4.3 | User Acceptance and Testing for MOH Reports | Test Results Report for MOH Reports | Jembi | FGH/MOH | not started | [12 empty] | x | x
ETPS Cosmetic | 5.1 | Update ETPS Banner | OpenMRS package with banner updated | Jembi | FGH | not started | [11 empty] | x
ETPS Package Deployment | 6.1 | Develop and deliver distribution MasterCard Scripts (for OpenMRS 1.11.x) | OpenMRS package with MasterCard and Reports Distributed | Jembi | FGH | not started | [11 empty] | x
| 6.2 | Deployment to health facilities | OpenMRS package with MasterCard and Reports Deployed | Partners | Jembi | not started
| 6.3 | Release of notes, training and user guides | Update training materials, notes and user guides for EPTS | Jembi | Partners/MISAU | not started | [12 empty] | x | x

## Sheet1
The MER report changes fall into the EPTS work plan which FGH is leading for OpenMRS v1.11.6, and it will be delivered along with the MasterCard package. The Jembi development and BA team are working with FGH to action this.
The first step is to understand the impact of the MasterCard changes and how that will affect all the other forms and reports (MER reports included). FGH and Paulo are currently performing that mapping exercise and should be done within the next week or so.
activities changes are in red color;
- delayed timeline in red color;
- extended timeline in yellow color;
- status updated;
- TLD requirement added;
- 1.9.2 development removed;
- reporting module added;
Please let us know if any additional update is required or any concern exists that need to be addressed.
We will update about the status and any timeline issue every Thursday.